BOXDSEATS

Implementation Roadmap

Build Sequence, Dependencies & Sprint Plan

Version 1.0 — February 2026

# 1. Executive Summary

This roadmap sequences the BoxdSeats build into concrete phases and sprints. Each sprint has a clear deliverable that can be tested independently. The goal is to reach a testable MVP in 8–10 weeks of solo development.

| Phase | Focus | Duration | Outcome |
| --- | --- | --- | --- |
| Phase 0 | Foundation & Data Seeding | 2 weeks | Database running, reference data seeded, auth working |
| Phase 1 | Core Loop (Log → Timeline → Profile) | 3 weeks | A user can sign up, log events, and view their timeline |
| Phase 2 | Venues, Explore & Polish | 2 weeks | Venue pages, search, venue map, shareable profiles |
| Phase 3 | Social Features | 2 weeks | Follows, social feed, likes, comments, companion tags |
| Phase 4 | Lists, Badges & Launch Prep | 1–2 weeks | System lists, badges, empty states, OG images, deploy |
| Post-MVP | Notifications, Stats, Native App | Ongoing | Phase 2/3 PRD features |

Critical path: Phase 0 → Phase 1 is the only hard dependency chain. Phases 2, 3, and 4 can be parallelized or reordered, though the sequence above is recommended because venue pages and search improve the event logging experience, and social features need content to be meaningful.

Solo developer estimate: 8–10 weeks of focused work, assuming nights/weekends at ~15–20 hours/week, or 4–5 weeks at full-time pace.

# 2. Phase 0 — Foundation & Data Seeding (2 Weeks)

Phase 0 produces no user-facing UI. Its job is to establish the development environment, database, and seed data so that all subsequent phases can build on real data from day one.

## 2.1 Sprint 0A — Project Setup (Days 1–3)

| Task | Details | Depends On | Done When |
| --- | --- | --- | --- |
| Initialize Next.js project | npx create-next-app@latest with App Router, TypeScript, Tailwind, ESLint | Nothing | npm run dev shows welcome page |
| Initialize Supabase project | Create Supabase project (cloud). Install Supabase CLI. Run supabase init locally. | Nothing | supabase start launches local stack |
| Apply database schema | Copy boxdseats-schema.sql to supabase/migrations/. Run supabase db reset. | Supabase project | All 25 tables created, RLS policies active |
| Add external_ids column | Add external_ids JSONB to events, teams, venues, athletes tables. Create migration. | Schema applied | Migration applies cleanly |
| Configure Supabase Auth | Enable email/password, Google OAuth, Apple OAuth in Supabase Dashboard. | Supabase project | Can sign up via email in Supabase Studio |
| Connect Next.js to Supabase | Install @supabase/supabase-js + @supabase/ssr. Create browser and server clients. Add middleware for session refresh. | Both projects created | Server Component can query leagues table |
| Set up Vercel deployment | Connect GitHub repo to Vercel. Set environment variables. First deploy. | Next.js project | Production URL returns the welcome page |
| Generate TypeScript types | Run supabase gen types typescript --local. Verify typed client works. | Schema applied | IDE autocomplete shows table/column names |

## 2.2 Sprint 0B — Data Seeding (Days 4–10)

This is the most time-intensive sprint in Phase 0. The seeding scripts create the reference data that every other feature depends on. Seed in dependency order.

### 2.2.1 Seeding Order & Dependencies

| Step | Script | Source | Volume | Est. Time | Depends On |
| --- | --- | --- | --- | --- | --- |
| 1 | seed-leagues.ts | Manual JSON fixture | 10 rows | 30 min | Schema |
| 2 | seed-teams.ts | BDL Teams API (all 8 leagues) | ~150 teams | 2 hours | Leagues seeded, BDL free account |
| 3 | seed-venues.ts | SeatGeek API + ESPN Venues | ~350 venues | 3 hours | Teams seeded (for venue-team mapping) |
| 4 | seed-venue-aliases.ts | Manual JSON fixture | ~100 aliases | 1 hour | Venues seeded |
| 5 | seed-athletes.ts | BDL Players API | ~5K active (skip full 20K for MVP) | 2 hours | Teams seeded |
| 6a | seed-events-bdl.ts (Big 4) | BDL Games API: NBA, NFL, MLB, NHL | ~130K events | 3–4 hours (ALL-STAR tier) | Teams + venues seeded |
| 6b | seed-events-bdl.ts (MLS/PGA/Tennis) | BDL Matches/Tournaments API | ~15K events | 1 hour | Same as 6a |
| 6c | seed-events-espn.ts | ESPN Scoreboard API | NFL 2000–2001 backfill + venue enrichment | 2 hours | 6a done (needs gaps identified) |
| 6d | seed-events-nascar.ts | SportsDataIO (or manual JSON) | ~625 races (2000–2025) | 2 hours | Leagues seeded |
| 6e | seed-events-indycar.ts | Manual JSON fixture | ~425 races | 3 hours (manual data entry) | Leagues seeded |
| 7 | seed-lists.ts | Manual JSON fixture | ~20 system lists + items | 1 hour | Events + venues seeded |
| 8 | seed-badges.ts | Manual JSON fixture | ~15 badges | 30 min | Nothing (standalone) |
| 9 | validate.ts | Cross-reference queries | N/A | 30 min | All above |

Total estimated seeding time: About 20 hours of developer time (writing scripts + running + debugging). The scripts themselves run in 2–4 hours once written, assuming BDL ALL-STAR tier for bulk fetching.

BDL API cost for seeding: Purchase one month of ALL-STAR for the 4 Big 4 leagues ($9.99 × 4 = $39.96) to get 60 req/min rate limit. Downgrade to free after seeding completes. PGA + ATP + WTA seeding requires ALL-STAR ($9.99 × 3 = $29.97) since free tier doesn’t include results.

MVP scope reduction option: If seeding all 10 leagues is too much for initial development, seed only NFL + NBA + MLB + NHL (Big 4) first. Add remaining leagues after the core loop is working. This cuts seeding time roughly in half.

Deferred seeding (athlete-level data): Three junction tables — athlete_teams (roster history), event_athletes (field event finishers), and event_rosters (match event starters) — are not seeded for MVP. They require per-game roster data which significantly increases API calls and complexity. The core logging experience works without them; they primarily support Stats Deep Dive (Phase 2 PRD feature).

### 2.2.2 Validation Checks

The validate.ts script runs these checks after all seeding completes:

Orphan check: Events with home_team_id or away_team_id not in teams table.

Venue coverage: Events with null venue_id. Acceptable for some neutral-site games but should be < 5% overall.

External ID uniqueness: No duplicate external_ids within a provider.

Date sanity: No events before year 2000 or after current date.

League completeness: Each league has at least 1 season of events.

## 2.3 Phase 0 Exit Criteria

Phase 0 is complete when all of the following are true:

1. supabase db reset applies cleanly. All 25 tables, RLS policies, triggers, and indexes created.

2. At least the Big 4 leagues are seeded with teams, venues, and events from 2002–present.

3. A Next.js Server Component can query events with joins to leagues, teams, and venues, and display results.

4. Supabase Auth sign-up/login works via email. Profile trigger creates a profiles row automatically.

5. Vercel deployment succeeds and serves the app at a public URL.

6. TypeScript types are generated and the Supabase client is fully typed.

# 3. Phase 1 — Core Loop (3 Weeks)

Phase 1 builds the minimum path a user walks: sign up → onboard → log an event → see it on their timeline → view their profile. This is the core value proposition. Everything else builds on this loop.

## 3.1 Sprint 1A — Auth & Onboarding (Days 1–4)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| Login page | (auth)/login/page.tsx | Email/password form + Google/Apple OAuth buttons. Redirects to / on success. | User can log in and reach the app shell |
| Signup page | (auth)/signup/page.tsx | Email/password + OAuth. Email confirmation enabled. Triggers profile creation. | New user has a profiles row after signup |
| Auth middleware | middleware.ts | Refresh session, redirect unauth to /login, redirect no-profile to /onboarding. | Unauth users always land on login |
| Onboarding flow | (auth)/onboarding/page.tsx | Multi-step form: display name, username, avatar upload, select favorite leagues (optional). Writes to profiles table. | User completes onboarding and lands on home |
| App layout shell | (app)/layout.tsx | Bottom nav (5 tabs), auth check. Empty page stubs for all routes. | Nav renders, tabs navigate to stub pages |

## 3.2 Sprint 1B — Event Logging (Days 5–11)

This is the single most important feature. The logging flow should feel fast and satisfying.

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| Log entry page | (app)/log/page.tsx | Step 1: Select league (grid of 10 league cards). Step 2: Select date (date picker, defaults to today). Step 3: See matching events for that league + date. | User sees events for NFL on 2024-01-15 |
| Event selection | (app)/log/page.tsx | Display matching events as cards: home vs away, venue, time. User taps to select. | Selecting an event navigates to log form |
| Log form | (app)/log/[eventId]/page.tsx | Auto-populated: event details, venue, teams. User enters: personal note (textarea), rating (1–5), rooting interest (home/away/neutral), section/seat (text), privacy tier (select). Photo upload (optional). | Submitting creates an event_logs row |
| Photo upload | Component in log form | File input, client-side preview, upload to Supabase Storage event-photos bucket. Save public URL to event_log. | Photo appears in preview before submit |
| Manual entry fallback | (app)/log/page.tsx | Link at bottom: 'Can’t find your event? Log it manually.' Opens form with all fields editable (league, date, teams, venue). | User can log an event not in the database |
| Multi-day event handling | Logic in log flow | For field events (PGA, tennis, NASCAR, IndyCar): one event row per tournament/race. User logs attendance once and optionally notes which days attended. Match events are always single-day. PRD 5.7. | PGA tournament logs as a single event |
| Confirmation | Post-submit redirect | After logging, redirect to the event log detail or timeline with a success toast. | User sees their logged event immediately |

## 3.3 Sprint 1C — Timeline & Profile (Days 12–21)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| Timeline page | (app)/timeline/page.tsx | Reverse-chronological list of user’s event_logs with event details, venue, score, personal note, rating, photo. Paginated (20 per page). | User sees all their logged events |
| Timeline filters | Client component in timeline | Filter by league (dropdown), sport (dropdown), year (dropdown). Filters stored in URL search params. | Filtering shows subset of events |
| Event log card component | Shared component | Reusable card showing: league badge, event name (teams + score), venue, date, rating stars, personal note preview, photo thumbnail. Used in timeline, feed, profile. | Card renders correctly for all event types |
| Profile page (own) | (app)/profile/page.tsx | Header: avatar, display name, username, bio, event count, venue count, follower/following counts (0 for now). Big Five Favorites section. Below: timeline of logged events. | Profile shows correct counts and events |
| Big Five selection | Component in profile/settings | User can set their 5 favorites: team, athlete, venue, event, league. Each is a search-select input that queries the relevant table. | Favorites display on profile |
| Profile page (other user) | (app)/profile/[username]/page.tsx | Same layout but with follow button (disabled for now), respects privacy column on event_logs. | Can view another user’s public profile |
| Edit/delete event log | Actions on event log card | Edit: opens prefilled log form. Delete: confirmation dialog then remove. Both via Server Actions. | User can modify their logged events |
| Event detail page | (app)/event/[eventId]/page.tsx | Shows event info: teams, score, venue, date, league. Below: list of users who logged this event (attendance count, respecting privacy). | Event page shows who attended |

## 3.4 Phase 1 Exit Criteria

1. A new user can sign up, complete onboarding, and reach the home page.

2. User can log an event in under 60 seconds (league → date → event → details → submit).

3. Timeline displays all logged events with correct event data, venue, and personal details.

4. Profile shows event count, venue count, Big Five favorites, and recent timeline.

5. Another user’s public profile is viewable at /profile/[username] with privacy tiers enforced.

6. Event logs can be edited and deleted by the owner.

# 4. Phase 2 — Venues, Explore & Polish (2 Weeks)

Phase 2 adds the venue experience (a key differentiator for BoxdSeats) and the explore/search functionality that makes the app navigable at scale.

## 4.1 Sprint 2A — Venue Pages & Map (Days 1–7)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| Venue detail page | (app)/venue/[venueId]/page.tsx | Header: name, city/state, capacity, status (active/retired/demolished). Map pin. Teams that play here. Events held here (paginated). Users who visited. | Venue page renders with real data |
| Venue map | Component (Mapbox GL or Leaflet) | Interactive map showing all venues as pins, colored by sport. User’s visited venues highlighted differently. Click pin → navigate to venue page. | Map renders with ~350 venue pins |
| Venue marking | Button on venue page | Mark as 'visited' or 'want to visit' independent of event logging. Writes to venue_visits table. | Marking a venue updates the map |
| Venue map on profile | Component on profile page | Small map showing user’s visited venues. Compact version of the full venue map. | Profile shows visited venue pins |
| Venue aliases / historical names | Display on venue page | Show current name + historical names with date ranges. 'You attended a game here when it was called...' | Historical venue name displays correctly |
| Retired/demolished venues | Visual treatment | Gray styling for retired venues, distinct indicator for demolished. No event logging for demolished venues. | Retired venues visually distinct |

## 4.2 Sprint 2B — Explore & Entity Pages (Days 8–14)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| Explore/Search page | (app)/explore/page.tsx | Search bar with unified results across venues, teams, athletes, users. Results grouped by type. Uses ilike for fuzzy matching. | Searching 'Fenway' returns the venue and Red Sox |
| Team detail page | (app)/team/[teamId]/page.tsx | Team name, logo, league, home venue. Events list (paginated). Users who attended most games. | Team page shows real data |
| Athlete detail page | (app)/athlete/[athleteId]/page.tsx | Name, team(s), sport. Minimal for MVP — primarily a linkable entity for Big Five favorites. | Athlete page renders |
| League detail page | (app)/league/[leagueSlug]/page.tsx | League name, teams list, upcoming events, recent results. | League page shows teams and events |
| Settings page | (app)/settings/page.tsx | Edit profile (display name, username, bio, avatar). Privacy toggle (public/private). Big Five management. Sign out button. | User can update their profile settings |
| Loading & error states | loading.tsx + error.tsx per route | Skeleton loading states for timeline, profile, venue pages. Error boundaries with retry button. | Loading states visible on slow connections |
| Empty states | Per-page components | Custom empty state messages and CTAs for timeline, feed, lists, search results, notifications. | Every list view has a meaningful empty state |

## 4.3 Phase 2 Exit Criteria

1. Venue pages display real data including historical names, home teams, and visitor list.

2. Venue map renders all seeded venues with sport-based color coding.

3. Search returns relevant results across all entity types within 500ms.

4. All entity pages (team, athlete, league) are functional and linked from event logs.

5. Settings page allows full profile editing including avatar upload.

6. Every page has a loading state and error boundary.

# 5. Phase 3 — Social Features (2 Weeks)

Phase 3 adds the social layer that makes BoxdSeats sticky. Without social, the app is a personal journal. With social, it becomes a community.

## 5.1 Sprint 3A — Social Graph (Days 1–7)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| Follow/unfollow | Button on profile pages | Public profiles: follow is instant. Private profiles: sends follow request. Unfollow is always instant. Updates follows table. | Can follow/unfollow any user |
| Follow requests | Section in notifications or settings | Pending follow requests shown to the target user. Accept/reject actions update follows.status. | Private profile user can accept/reject requests |
| Follower/following lists | Modal or sub-page on profile | Tappable lists of followers and following. Each entry links to that user’s profile. | Lists show correct counts and navigate |
| Block user | Action in profile menu | Creates blocks row. Blocked user can’t see your content, follow you, or appear in your feed. | Blocked user sees nothing from you |
| Social feed (home page) | (app)/page.tsx | Reverse-chronological feed of event_logs from followed users. Respects privacy tiers. Uses event log card component from Phase 1. | Feed shows followed users’ activity |
| Feed real-time updates | Supabase Realtime subscription | Subscribe to event_logs changes for followed users. New logs appear at top of feed without refresh. | New log appears live within seconds |
| Profile discovery | Section in explore page | Suggested users: friends of friends, users who attend same events, popular users. Basic implementation. | Explore page suggests relevant users |

## 5.2 Sprint 3B — Interactions (Days 8–14)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| Likes | Button on event log card | Toggle like/unlike. Optimistic UI. Updates likes table. Shows like count. | Tapping heart toggles like with animation |
| Comments | Section under event log card | Text-only comments. Expandable comment section. Delete own comments. | Can comment on any visible event log |
| Companion tagging | Component in log form | Search-select input to tag friends who attended with you. Creates companion_tags rows. Tagged user gets notification. | Companion names appear on event log card |
| Activity counts | Profile header | Update profile to show accurate counts: events logged, unique venues, followers, following. | All counts are correct and update in real-time |
| Report content | Action in overflow menu | Report event logs, comments, or users. Creates reports row. No admin panel yet — check via Supabase Studio. | Report button works on all content types |
| Share profile link | Share button on profile | Copies shareable URL to clipboard. Profile URL works for logged-out users (public profiles only). | Shared link shows profile to non-users |

## 5.3 Phase 3 Exit Criteria

1. Complete follow/unfollow/request cycle works for public and private profiles.

2. Social feed shows followed users’ event logs with real-time updates.

3. Likes, comments, and companion tags work with proper notification triggers.

4. Block and report functionality prevents unwanted interactions.

5. Profile sharing works for non-authenticated users.

# 6. Phase 4 — Lists, Badges & Launch Prep (1–2 Weeks)

Phase 4 adds the collectibility layer and prepares the app for real users.

## 6.1 Sprint 4A — Lists & Badges (Days 1–7)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| System lists display | (app)/lists/page.tsx | Show pre-seeded system lists: 'Every NFL Stadium', 'Every MLB Ballpark', etc. User’s progress shown as fraction and progress bar. | Lists page shows system lists with progress |
| List detail page | (app)/lists/[listId]/page.tsx | All items in list with visited/not-visited status. Items link to venue or event pages. | Can see which items are complete |
| User-created lists | Create list form | Users can create venue lists or event lists. Add items from search. Reorder items. | Can create and manage custom lists |
| List following | Button on list detail | Follow another user’s list. Shows in your lists page under 'Following'. | Can follow and track progress on others’ lists |
| Badge system | (app)/badges/page.tsx | Display earned and locked badges. Earned badges show date and triggering event. Badge earning triggered by database functions checking conditions. | Badges display and unlock correctly |
| Badge triggers | Database functions | Implement key badge rules: first event logged, 5/10/25/50/100 events, every stadium in a league, first companion tag, etc. | Badges auto-award on qualifying actions |

## 6.2 Sprint 4B — Launch Prep (Days 8–14)

| Task | Route/Component | Details | Done When |
| --- | --- | --- | --- |
| OG images | api/og/[type]/[id]/route.ts | Dynamic Open Graph images for profiles, events, and venues. Branded card with BoxdSeats logo, entity details, stats. | Sharing a profile URL shows a rich preview |
| SEO metadata | generateMetadata per page | Page titles, descriptions, and OG images for all entity pages. Site-wide defaults in root layout. | Google shows correct title/description |
| Edge Function sync setup | supabase/functions/ | Deploy at least one sync function (e.g., sync-nba-results). Set up pg_cron schedule. Verify daily sync runs. | Yesterday’s NBA games appear in database automatically |
| Performance audit | Lighthouse + manual testing | Run Lighthouse on key pages. Fix any issues above ‘good’ threshold. Optimize images, eliminate layout shift. | All pages score 90+ on Lighthouse mobile |
| Cross-browser testing | Manual testing | Test on Chrome, Safari (iOS), Firefox. Verify bottom nav, map, photo upload, auth flow on mobile. | No critical bugs on major browsers |
| Error monitoring | Vercel Analytics + manual | Enable Vercel Analytics. Test error boundaries. Verify Edge Function logging. | Errors are visible and debuggable |
| Seed production database | Run seed scripts against prod | Apply migrations to production Supabase. Run seed scripts. Validate. | Production has same reference data as local |
| Domain & DNS | Vercel custom domain | Connect custom domain (if desired). Configure SSL. | App accessible at custom URL |

## 6.3 Phase 4 Exit Criteria (= MVP Launch Criteria)

1. A new user can sign up, complete onboarding, log 3+ events, and share their profile in one session.

2. The logging flow takes under 60 seconds from tap to confirmation.

3. Profile looks impressive with logged events, venue map, and Big Five favorites.

4. Social features work end-to-end: follow, feed, like, comment, companion tag.

5. System lists show meaningful progress tracking.

6. OG images generate correctly for profile sharing.

7. At least one Edge Function syncs new event results daily.

8. No critical bugs on mobile Safari and Chrome.

# 7. Post-MVP Features (Prioritized Backlog)

These features are defined in the PRD but explicitly deferred past MVP launch. They are ordered by expected impact.

| Priority | Feature | PRD Section | Complexity | Impact | Notes |
| --- | --- | --- | --- | --- | --- |
| P1 | Notifications (in-app) | 11.1–11.2 | Medium | High | Database triggers already exist. Build notification bell + list page. |
| P2 | Stats Deep Dive | 12.1–12.6 | High | High | Requires multiple RPC functions. Frequency, outcome, venue, completion stats. |
| P3 | Ongoing sync for all 10 leagues | Data Strategy 4.3 | Medium | Medium | Deploy remaining Edge Functions. Verify pg_cron for each league. |
| P4 | Notification preferences | 14.3 | Low | Medium | Per-type toggles. notification_preferences table already exists. |
| P5 | Year-in-Review | 12.7 | High | High | Annual summary. Phase 3 feature. Build after Stats foundation. |
| P6 | Milestone Stats | 12.4 | Medium | Medium | 100th game, every stadium, streak tracking. Phase 3 feature. |
| P7 | Push notifications | 11 (implied) | Medium | Medium | Requires native app or PWA service worker. |
| P8 | Native mobile app | PRD 2.1 | Very High | High | React Native. Reuse Supabase client and API patterns. |
| P9 | Admin dashboard | Implied | Medium | Low | Content moderation, report review, data quality monitoring. |
| P10 | User-contributed venue photos | 7.4 (implied) | Low | Low | Additional storage bucket, moderation workflow needed. |

# 8. Dependency Graph

This section maps the hard dependencies between tasks. A task cannot start until its dependencies are complete.

## 8.1 Critical Path

The longest chain of dependent tasks determines the minimum build time:

Schema → Seed leagues → Seed teams → Seed venues → Seed events → Event logging UI → Timeline UI → Profile UI → Social feed → MVP

This chain is approximately 8 weeks. No parallelization can shorten it because each step requires the output of the previous step.

## 8.2 Parallelizable Work

These tasks can be done alongside the critical path:

During seeding (Phase 0B): Auth UI, onboarding flow, app layout shell, bottom nav. These don’t need seed data.

During core loop (Phase 1): Venue map component (can use test data). Badge definitions (manual JSON). System list definitions (manual JSON).

During venue work (Phase 2): OG image generation. SEO metadata. Loading/error states.

During social (Phase 3): Edge Function development. Launch prep tasks.

## 8.3 External Dependencies

| Dependency | Needed By | Lead Time | Risk | Mitigation |
| --- | --- | --- | --- | --- |
| BDL API key (free) | Phase 0B (seeding) | Instant (self-service) | None | Sign up at app.balldontlie.io |
| BDL ALL-STAR tier | Phase 0B (bulk seeding) | Instant (self-service) | Low ($40–70) | Cancel after seeding month |
| SportsDataIO trial key | Phase 0B (NASCAR seeding) | 1–2 days (application) | Medium | Manual JSON fallback if denied |
| Google OAuth credentials | Phase 1A (auth) | 1–2 hours (Google Cloud Console) | None | Standard setup process |
| Apple OAuth credentials | Phase 1A (auth) | 1–2 days (Apple Developer account) | Low | Skip for MVP, add post-launch |
| Mapbox/Leaflet token | Phase 2A (venue map) | Instant (self-service) | None | Mapbox free tier: 50K map loads/mo |
| Custom domain | Phase 4B (launch) | 1–24 hours (DNS propagation) | None | Can launch on vercel.app domain first |

# 9. Risk Register

| Risk | Likelihood | Impact | Phase Affected | Mitigation |
| --- | --- | --- | --- | --- |
| BDL API changes or goes down | Low | High | Phase 0B, ongoing | External IDs enable provider swap. ESPN API as backup for Big 4. |
| Seeding takes longer than estimated | Medium | Medium | Phase 0B | Reduce MVP scope to Big 4 only. Add other leagues post-launch. |
| Supabase free tier limits hit | Low | Medium | Phase 4+ | Monitor usage. Upgrade to Pro ($25/mo) when needed. |
| Venue geocoding data quality | Medium | Low | Phase 2A | SeatGeek provides lat/lng data for the location column. Manual correction for outliers. |
| RLS policy bugs leak private data | Low | Critical | All phases | Write RLS integration tests in Phase 1. Test every policy. |
| Photo upload fills storage | Low | Low | Phase 1B+ | 5MB limit per photo. Monitor storage. Add cleanup job if needed. |
| Edge Function sync failures | Medium | Low | Phase 4B+ | Health check query surfaces stale data. Manual re-run as fallback. |
| Scope creep delays MVP | High | High | All phases | This roadmap defines MVP scope. Defer everything to post-MVP backlog. |

# 10. Effort Estimates

Estimates assume a solo developer familiar with Next.js, Supabase, and TypeScript. Add 50% buffer for learning curve if any technology is new.

| Sprint | Calendar Days | Dev Hours | Key Deliverable |
| --- | --- | --- | --- |
| 0A: Project Setup | 3 days | 8–12 hours | Running Next.js + Supabase + Vercel pipeline |
| 0B: Data Seeding | 7 days | 15–20 hours | Database populated with 130K+ events |
| 1A: Auth & Onboarding | 4 days | 10–15 hours | User can sign up and complete onboarding |
| 1B: Event Logging | 7 days | 15–20 hours | User can log events with all fields |
| 1C: Timeline & Profile | 10 days | 20–25 hours | Timeline, profile, event pages all working |
| 2A: Venues & Map | 7 days | 15–20 hours | Venue pages and interactive map |
| 2B: Explore & Polish | 7 days | 15–20 hours | Search, entity pages, loading states |
| 3A: Social Graph | 7 days | 15–20 hours | Follow system and social feed |
| 3B: Interactions | 7 days | 12–18 hours | Likes, comments, companion tags |
| 4A: Lists & Badges | 7 days | 15–20 hours | System lists with progress, badge system |
| 4B: Launch Prep | 7 days | 12–18 hours | OG images, SEO, sync, testing, deploy |
| TOTAL | ~73 days (~10 weeks) | 142–208 hours | Complete MVP |

Part-time pace (15–20 hrs/week): 10–14 weeks to MVP.

Full-time pace (40 hrs/week): 4–5 weeks to MVP.

Realistic estimate with debugging and rework: Add 20–30% buffer. Part-time: 12–16 weeks. Full-time: 5–7 weeks.

# 11. Quick Start Checklist

Do these things today to unblock Phase 0:

1. Sign up for a BDL free account at app.balldontlie.io. Test the NBA Games endpoint.

2. Create a Supabase project at supabase.com.

3. Create a GitHub repository for boxdseats.

4. Run npx create-next-app@latest boxdseats (TypeScript, App Router, Tailwind, ESLint).

5. Connect the repo to Vercel for auto-deployment.

6. Copy boxdseats-schema.sql into supabase/migrations/ and run supabase db reset.

7. Write and run seed-leagues.ts with the 10 league records.

8. You are now in Phase 0. Start Sprint 0A.

# 12. Companion Documents

This roadmap references and depends on:

BoxdSeats Brand Guide: Visual identity, color system, typography.

BoxdSeats PRD v1.3: Complete product requirements (607 paragraphs).

BoxdSeats Data Model v1.0: Database schema (25 tables, boxdseats-schema.sql).

BoxdSeats API & Data Strategy v1.2: Data sources, provider evaluation, ingestion patterns.

BoxdSeats Technical Architecture v1.1: Infrastructure, services, deployment, query patterns.

BoxdSeats Implementation Roadmap v1.0: This document.